# Management Plan

- Key project personnel and adequacy of time commitments of key personnel in meeting objectives:

1.  Project /Practice Management – As a full time employee, the Project Director represents the Senior Staff management.  He or she will be directly accountable to the Partnership Steering Committee for all aspects of program management, including agency and community relationships, budget administration, health and safety and conduct.  The Project Director is responsible for planning, implementing and evaluating the program, supervising staff and enhancing relationships with partner agencies.  The Senior Staff team has the opportunity to define their working relationship and divide tasks and responsibilities according to skill and interests.

2.  GEAR-UP Liaison will provide faculty level support and guidance to the project director in their work to coordinate activities among the multiple partners, students, and their mentors.

Partner responsibilities: Partner responsibilities include the general requirements listed below and those listed specifically in the implementation timeline (C).

- Communicate with school and project management

- Coordinate activities with staff and volunteers

- Reporting early challenges in implementation

C.  Adequacy of plan to achieve quantifiable objectives on time and within budget

| Implementation Tasks | Timeline | Responsible Party | Collaboration |
| --- | --- | --- | --- |
| Advertise and hire new staff | First 60 days | SBSAS Executive Director | SBSAS Program Partners |
| Train all staff on new program requirements | Month 3 | SBSAS Program Director | SBSAS Project Coordinator |
| Introduce SBSAS Program to partnership schools | October 2008-December 2008 | SBSAS Program Director | Harrisonburg City, Page & Rockingham County Public Schools |
| Recruit volunteer mentors | October 2008 & ongoing through 2014 | SBSAS Program Director | Partners: Community Churches, Civic Groups, Businesses and Universities |
| Identify greatest need students and have referrals ready for SBSAS mentors | October 2008 and ongoing through 2014 | Teachers, Guidance Counselors & Liaisons at Schools | SBSAS- Match Support Specialists |
| Screen Potential Mentors | October 2008 and ongoing through 2014 | SBSAS Program Director | Partners: Community Churches, Civic Groups, Businesses and Universities |
| Establish SBSAS Program at designated schools | November 2008-October 2009 | SBSAS Project Coordinator | Program Director, Harrisonburg, Page & Rockingham County Public Schools |
| Orient and train new mentors | October 2008 and ongoing through 2014 | SBSAS Project Coordinator | School Staff |
| Plan and coordinate campus visits to partner higher education institutions | October 2008 and ongoing through 2014 | SBSAS Program Director | All partner entities |
| Provide ongoing support training (all three years) | January 2009 (6 times per year) through 2014 | SBSAS Project Coordinator | Community Educators |
| Survey parents to determine collaboration opportunities | September 2008 and ongoing through 2014 | SBSAS Project Coordinator | All partner entities |
| Recruit and train mentors interested in transferring to SBSAS from current school base program | Begin in November 2008 | Match Support Specialists & SBSAS Project Coordinator | SBSAS - Enrollment Specialists |
| Identify ‘match goals’ for each child | Begin in November 2008 and ongoing as youth are matched through 2014 | Match Support Specialists | Teachers & Guidance Counselors |
| Provide parental outreach and training workshops | November 2008 and ongoing through 2014 | SBSAS Program Coordinator | SBSAS partner entities |
| Match mentors and students | January 2009 and ongoing through 2014 | School Liaisons & Match Support Specialists | SBSAS - Enrollment Specialists |
| Provide regular match support | Monthly 2008-2014 | Match Support Specialists | SBSAS -Volunteers, Parents & Youth |
| Communicate grant progress with SBSAS program partners | Quarterly 2008-2014 | Program Director | Schools & Project Evaluator |
| Collect pre and post data re: core academic grades and attendance | Twice per year 2008-2014 | SBSAS Project Coordinator & School Liaisons | Project Evaluator |
| Send, collect and assess Program Outcome Evaluation (POE) Surveys, to teachers | April, each year 2008-2014 | Match Support Specialists | Parents, School Liaison & Teachers |
| Complete performance evaluation and give to SBSAS | As per grant report guidelines 2008-2014 | Project Evaluator | SBSAS |
| Share SBSAS Outcomes with DOE | As per grant report guidelines 2008-2014 | SBSAS Project Coordinator | SBSAS - Program Director |
| Develop projected 6 year annual calendar of events and enrichment activities | Winter 2008-08 | SBSAS Project Coordinator | SBSAS -Program Director & Match Support Specialists |

# D. Adequacy of procedures for ensuring feedback, data collection, and continuous improvement among the project partners.  The project will use a comprehensive set of standardized procedures and tools to evaluate program objectives. The Performance-based Outcome Evaluation (POE) is a survey instrument used to assess outcomes for multiple indicators. For school-based programs, parents, mentors, and teachers complete an annual POE evaluation of the student. Data collected can be used in the assessment of individual matches as well as overall program results. A recent POE summary of local school-based matches is located at Appendix G.  Partners will collect, track and report relative data to the program director on a quarterly basis.  This data will measure performance from initial inquiry to match closure and assists program leadership in monitoring individual and agency match progress and performance and compare it against national performance data. The program director will closely monitor and disseminate trend data to the Partners – ensuring both positive and negative trends are analyzed and disseminated.